## Slide 1
26 APRIL 2026
Progress Review
Observability for Autoscaling Correctness in Kubernetes-Based Systems
By S.A.C.S. Indrejith - 2020ICT65
Supervisor: Ms. R. Yasotha, Senior Lecturer Gr. II, Department of Physical Science.
Co-Supervisor: Mr. Suvin Kodituwakku, Senior Software Engineer, WSO2 Lanka Pvt Ltd.

## Slide 2
02
Research Problem
Autoscaling systems lack mechanisms to evaluate decision effectiveness.
What we CAN see
How many pods were created
CPU and memory usage per pod
Application latency from logs
Source: Standard Kubernetes telemetry - HPA status API, Metrics Server, and kubelet logging (Kubernetes Documentation, 2026).
What we CANNOT tell
Was scaling really needed at that moment?
Did it happen on time?
Did it actually fix the problem, or was it useless?
Evidence: Xu et al. (2025) survey of cloud-native autoscaling notes no framework exists for decision-level correctness; Silva et al. (2025) finds observability research treats control actions as opaque events, not analysable entities.
This lack of decision-level, outcome-oriented feedback makes it difficult to assess autoscaler behavior, tune configurations, or identify resource inefficiencies.

## Slide 3
03
Why is this research needed?
Kubernetes HPA already scales automatically - so what's missing?
HPA does this
Watches CPU and memory utilisation
Scales pods up when a threshold is breached
Scales pods down when usage drops
HPA does NOT do this
Tell you if each scaling action was needed
Tell you if the action arrived on time
Tell you if the action actually improved latency
Result for operators
Tuning thresholds becomes trial and error
Wasted resources go undetected
Missed SLOs cannot be traced to a decision
This research adds decision-level correctness as a first-class observability signal.

## Slide 4
04
Research Objectives & Scope
General Objective
To evaluate the correctness of autoscaling decisions in Kubernetes-based systems using observability-driven outcome-oriented metrics.
Scope
Kubernetes Horizontal Pod Autoscaler (HPA) only
Single-node experimental cluster
Four controlled workload patterns
Descriptive analysis of captured decisions
Specific Objectives
1. Define measurable criteria for classifying scaling decisions as correct or incorrect.
2. Design observability-based metrics for effectiveness, timeliness, and necessity.
3. Empirically evaluate Kubernetes HPA behavior under controlled workloads.
4. Analyze the relationship between individual decisions and SLO outcomes.

## Slide 5
05
Experiment Design
How correctness is measured per scaling decision
1
Inject workload
One of 4 controlled patterns: Step, Burst, Gradual Ramp, Noisy.
2
Capture decision
Side-channel watcher records every HPA replica change with timestamp + trigger metric.
3
Measure two signals
Timeliness: gap between SLO at risk and HPA action.
Effectiveness: latency before vs after action.
4
Classify decision
Correct & Timely / Correct but Late / Unnecessary / Ineffective.
Data sources: k6 load generator (workload), HPA Decision Watcher (decisions), Prometheus + service audit logs (latency for SLO + effectiveness measurement).

## Slide 6
06
Progress to Date
Methodology Phases
Phase 1: Experimental Setup
Complete
Phase 2: Application Under Test
Complete
Phase 3: Workload Generation
Scripts ready
Phase 4: Observability Collection
Complete
Phase 5: Capturing Decisions
Complete
Phase 6: Correctness Metrics
Pending
Phase 7: Analysis & Evaluation
Pending
Concrete Deliverables Built
Single-node Kubernetes cluster (HPA enabled)
Stateless Ballerina HTTP microservice with CPU-proportional load endpoint
Prometheus + Grafana monitoring stack (kube-prometheus-stack)
Custom HPA Decision Watcher (Python) emitting structured JSON events
Four k6 load-generation scripts: Step, Burst, Ramp, Noisy
Two real scaling decisions captured during pipeline validation

## Slide 7
07
Planned vs Actual Progress
As of 26 April 2026
Workstream | Planned (per Gantt) | Actual | Status
Title selection | Nov 2025 | Done | On track
Proposal | Dec 2025 | Done | On track
Literature Review | Dec 25 - May 26 | Ongoing | On track
Resource gathering | Jan - Feb 2026 | Done | On track
Tools and Techniques | Jan - Feb 2026 | Done | On track
Implementation | Feb - Apr 2026 | Phases 1, 2, 4, 5 complete; Phases 3, 6, 7 ahead | On track
Documentation Writing | Jan - May 2026 | Not yet started | Behind
Publication | May 2026 | Not yet due | Upcoming
Presentation & Submission | Jun 2026 | Not yet due | Upcoming
Action: catch-up plan for Documentation Writing - first chapter draft begins immediately after Phase 6 metrics are computed.

## Slide 8
08
Remaining Work
1
Execute workload campaign
Run 20 iterations per pattern (Step, Burst, Ramp, Noisy) with idle gaps between runs; capture all HPA decisions.
Late April - Early May
2
Compute correctness metrics
Implement analysis script to derive timeliness and effectiveness scores per scaling decision from captured data.
Early May
3
Decision classification & comparative analysis
Classify each decision into the four correctness categories; compare HPA behavior across the four workload patterns.
Mid May
4
Documentation writing
Draft Methodology, Results, and Discussion chapters in parallel with analysis; prepare publication draft.
May - June

## Slide 9
26 APRIL 2026
09
Thank You!
Questions & feedback welcome.